## Sheet1
Day | Date | Time Spent (Hours) | Description
1 | 2024-07-04 | 2 | Setup of ui, created the logo and changed it in all places of Nevsquare
2 | 2024-08-04 | 2 | Made login/signup page with some login functionality
3 | 30/4/2024 | 3.25 | Finished Login/SignUp/Forgot Password functionality in UI
4 | 2024-01-05 | 4.5 | Added user profile functionality with cool starting design
5 | 2024-08-05 | 5 | Finished Mostly User Basic profile update, password reset, email change
6 | 2024-10-05 | 1.5 | Added Username reset and integrated with new phases functionality on BE
7 | 19/5/2024 | 3 | Added categories in FE with design + Search Bar
8 | 22/5/2024 | 4.5 | Finished Product Add Page
9 | 23/5/2024 | 5 | Finished basically Product Page
10 | 24/5/2024 | 5 | Finished Update product + delete product + delete product by admin
11 | 25/5/2024 | 2.5 | Finished User Ban / Remove Ban functionality
12 | 26/5/2024 | 7 | Finished search, pagination, recommended products, my products, favorite products
13 | 27/5/2024 | 2 | Finsihed category search, user preview, final adjustments
|  | Total hours Spent | 47.25