## Sheet1
Day | Date | Time Spent (Hours) | Description
1 | 24/02/2024 | 5.35 | Created config server, organized potential microservices, did some tests
2 | 25/02/2024 | 5.4 | Updated Bff, created Rest template, a lot of stuff
3 | 26/02/2024 | 2.2 | Added product addition functionality
4 | 2024-01-03 | 4 | Worked on chat system, problem with Websocket.. still investigating
5 | 2024-04-03 | 8 | Finally solved chat system, will start working on the user details functionality, then on search
6 | 2024-07-03 | 4 | Thought of the new design using an Api Gateway
7 | 2024-08-03 | 6 | Added api Gateway, will test it tomorrow
8 | 2024-09-03 | 3 | Added caching mechanism
9 | 2024-10-03 | 2.5 | Added partial getUserDetails functionality
10 | 2024-11-03 | 2.5 | refactor and eliminate bff
11 | 2024-12-03 | 3 | Added hazelcast and configured some caching logic, started working on chat preview
12 | 13/3/2024 | 5 | Made chat preview and chat functionality
13 | 14/3/2024 | 5 | refactored cache and Added User Basic Details Update
14 | 15/3/2024 | 5 | Fight with cache second level
15 | 16/3/2024 | 6 | Finally optimized the cache in a great way, refactored user specific detail
16 | 17/3/2024 | 1 | Added UpdateProtectedUserDetails functionality
17 | 19/3/2024 | 3.16 | Added Product Category and Subcategory
18 | 20/3/2024 | 4 | Encoded chat messages
19 | 21/3/2024 | 8 | Added search engine functionality for products
20 | 22/3/2024 | 6.5 | Refactored search functionality, a lot of features added (category search, etc)
21 | 23/3/2024 | 1.15 | Added Admin Authority access on endpoint
22 | 25/3/2024 | 12 | Integrated Oauth2
23 | 26/3/2024 | 3.75 | Made Product Update functionality + a lot of refactoring
24 | 27/3/2024 | 2 | Added product like functionality, separated products retrieval by user
25 | 29/3/2024 | 5.4 | Added batch processing of data + product recommendations
| 29/3/2024 | 3 | added image to products + refactoring of update product functionality
26 | 30/3/2024 | 3.5 | enhanced registration process with email code registration + user image
27 | 31/3/2024 | 2.4 | Made cron job for registration codes removal after max 30 minutes of inactivity
| 31/3/2024 | 5 | Added Exception handling with custom error codes for better FE control over errors
28 | 2024-02-04 | 8 | Improved security a lot
| 2024-03-04 | 1.5 | Refactored search call method
| 2024-04-04 | 5 | Added User Ban and removed cron job ms, will have cron on each microservice
| 2024-05-04 | 4.5 | Configured correctly Oauth2 flow
29 | 28/4/2024 | 2 | Made swagger with auth header, password reset with security code
30 | 2024-10-05 | 5 | Changed User Protected Details update with process phases for better FE controll
|  | Total hours Spent | 153.81