## Sheet1
Day | Date | Time Spent (Hours) | Description
1 | 24/02/2024 | 5.35 | Created config server, organized potential microservices, did some tests
2 | 25/02/2024 | 5.4 | Updated Bff, created Rest template, a lot of stuff
3 | 26/02/2024 | 2.2 | Added product addition functionality
4 | 2024-01-03 | 4 | Worked on chat system, problem with Websocket.. still investigating
5 | 2024-04-03 | 8 | Finally solved chat system, will start working on the user details functionality, then on search
6 | 2024-07-03 | 4 | Thought of the new design using an Api Gateway
7 | 2024-08-03 | 6 | Added api Gateway, will test it tomorrow
8 | 2024-09-03 | 3 | Added caching mechanism
9 | 2024-10-03 | 2.5 | Added partial getUserDetails functionality
10 | 2024-11-03 | 2.5 | refactor and eliminate bff
11 | 2024-12-03 | 3 | Added hazelcast and configured some caching logic, started working on chat preview
12 | 13/3/2024 | 5 | Made chat preview and chat functionality
|  | Total hours Spent | 50.95